## Sheet1
Rockefeller Philanthropy Advisors
FSP Analytics Hub
FSP Analytics Hub
Timeline
Topic 1: Analysis of Downstream Customer Journey in East Africa
Milestone/Week | 2016-08-05 | 2016-08-12 | 2016-08-19 | 2016-08-26 | 2016-09-02 | 2016-09-09 | 2016-09-16 | 2016-09-23 | 2016-09-30
Kick-off/Initial Interviews | bar: 2016-08-05 to 2016-08-19
Data Collection/Normalization | bar: 2016-08-12 to 2016-08-26
Sources Review | bar: 2016-08-26
Advisors Review | bar: 2016-08-26 to 2016-09-02
Midpoint | bar: 2016-09-02
Prototype Building | bar: 2016-08-26 to 2016-09-16
Initial Modeling Ouput | bar: 2016-09-16
Write-up Reporting | bar: 2016-09-16 to 2016-09-23
Final (Manuscript + Presentation) | bar: 2016-09-16 to 2016-09-30
Not Started
In-Progress
Complete